## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | [Project's title] |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Planning a Literature Review
1.1 | Topic or area Overview | Vincent | 2022-05-05 | 2022-05-11 | 5 | 20% | bar: WEEK 1 R to WEEK 2 W
1.1.1 | Gernal research among target topics | Vincent | 2022-05-09 | 2022-05-13 | 5 | 0% | bar: WEEK 2 M to WEEK 2 F
1.2 | Define specific question: broad or narrow | Vincent | 2022-05-11 | 2022-05-13 | 3 | 0% | bar: WEEK 2 W to WEEK 2 F
1.3 | Problem review | Mata | 2022-05-16 | 2022-05-17 | 2 | 0% | bar: WEEK 2 W; WEEK 3 M to WEEK 3 T
1.4 | Fine tune the specific question | Vincent | 2022-05-17 | 2022-05-20 | 4 | 0% | bar: WEEK 2 W; WEEK 3 T to WEEK 3 F
1.5 | Project Initiation | Vincent | 2022-05-19 | 2022-05-20 | 2 | 0% | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
2 | Literature search
2.1 | Scope and Goal Setting | Vincent | 2022-05-23 | 2022-05-25 | 3 | 0% | bar: WEEK 2 W; WEEK 4 M to WEEK 4 W
2.2 | Define search methodology and checklist | Vincent | 2022-05-25 | 2022-05-27 | 3 | 0% | bar: WEEK 2 W; WEEK 4 W to WEEK 4 F
2.3 | Determine key words, phrases and sources of the searh area | Vincent | 2022-05-25 | 2022-05-27 | 3 | 0% | bar: WEEK 2 W; WEEK 4 W to WEEK 4 F
2.4 | Finding materials relevant to the problem | Vincent | 2022-05-30 | 2022-06-08 | 10 | 0% | bar: WEEK 2 W; WEEK 5 M to WEEK 6 F
2.5 | Literature finds review | Mata | 2022-06-02 | 2022-06-02 | 1 | 0% | bar: WEEK 2 W; WEEK 5 R
3 | Literature evaluation
3.1 | Determining which literature suit for the problem | Vincent | 2022-06-06 | 2022-06-17 | 10 | 0% | bar: WEEK 2 W; WEEK 7 M to WEEK 8 F
3.2 | Gap analysis from the Goal | Mata | 2022-06-13 | 2022-06-17 | 5 | 0% | bar: WEEK 2 W; WEEK 8 M to WEEK 8 F
3.3 | Final review of chose of Literature | Vincent | 2022-06-20 | 2022-06-24 | 5 | 0% | bar: WEEK 2 W; WEEK 9 M to WEEK 9 F
4 | Document
4.1 | Overall plan | Vincent | 2022-06-06 | 2022-06-17 | 10 | 0% | bar: WEEK 2 W; WEEK 6 M to WEEK 7 F
4.2 | Review rework | Vincent | 2022-07-03 | 2022-07-14 | 10 | 0% | bar: WEEK 2 W; WEEK 10 M to WEEK 11 F
4.3 | Final Review of report | Mata | 2022-07-06 | 2022-07-06 | 1 | 0% | bar: WEEK 2 W; WEEK 10 R
4.4 | Present results | Vincent | 2022-07-17 | 2022-07-21 | 5 | 0% | bar: WEEK 2 W; WEEK 12 M to WEEK 12 F
Formulas:
DUE DATE = [START DATE]+[DURATION]+1
DUE DATE = [START DATE]+[DURATION]-1
START DATE = [DUE DATE, row above]
START DATE = [START DATE, row above]