## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Color
CVD Mobile Healthcare Apps - Data Science Application Development
Sunderland Company Limited |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-07-04 |  |  |  |  | July | [27 empty] | August
Scrolling Increment: | 0 | time axis 2022-07-04 to 2022-08-28
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-07-04 to 2022-08-28
Initial Design Stage
Planning | On Track | Vincent | 100% | 2022-07-04 | 5
Gathering & Analysis of Requirement | On Track | Vincent | 100% | 2022-07-07 | 5
Template and Design | Med Risk | Jackie | 0% | 2022-07-12 | 5
Create the phototype | Milestone | Cedric | 0% | 2022-07-17 | 10 | bar: 2022-07-17 to 2022-07-26
Testing | Low Risk | Patrick | 0% | 2022-07-27 | 3
Fix period | Goal | Cedric | 0% | 2022-07-29 | 2 | 2022-07-29: 2; 2022-07-30: 2
Deployment Stage
Planning & Review | On Track | Vincent | 0% | 2022-07-31 | 2
Gathering Feedback & Re-Analysis of Requirement | Low Risk | Vincent | 0% | 2022-08-01 | 2
Fine Tune Design | Med Risk | Jackie | 0% | 2022-08-03 | 5
Implementation | On Track | Cedric |  | 2022-08-08 | 5
Testing & Integration | Milestone | Patrick |  | 2022-08-13 | 5 | bar: 2022-08-13 to 2022-08-17
Fix period | Goal | Cedric |  | 2022-08-15 | 3 | 2022-08-15: 2; 2022-08-16: 2; 2022-08-17: 2
Quality Control
Review & Improvement | On Track | Vincent |  | 2022-08-18 | 2
Gathering Feedback & Re-Analysis of Requirement | On Track | Vincent |  | 2022-08-19 | 2
Fine Tune Design | On Track | Jackie |  | 2022-08-20 | 3
Bug Fixes and Enhancements | Goal | Cedric |  | 2022-08-23 | 3 | 2022-08-23: 2; 2022-08-24: 2; 2022-08-25: 2
Final Testing | Goal | Patrick |  | 2022-08-26 | 2 | 2022-08-26: 2; 2022-08-27: 2
Launch | Goal |  |  | 2022-08-27
To add more data, Insert new rows ABOVE this one